## Risk register
ISO 27001 Risk Register
Information security risk assessment and treatment register ¦ Free template from ISOvault (isovault.co.uk)
Risk ID | Date raised | Risk description | Asset / process affected | CIA impact | Likelihood (1-5) | Impact (1-5) | Score | Rating | Risk owner | Treatment option | Linked Annex A controls | Treatment actions | Action due | Status | Next review
R-001 | 06/01/2026 | Laptop containing customer data lost or stolen while travelling | Staff laptops | C | 3 | 4 | 12 | Medium | IT Manager | Reduce | 8.1, 7.9, 8.24 | Full-disk encryption enforced by MDM; remote wipe enabled; clear desk policy | 31/01/2026 | Open | 06/07/2026
R-002 | 06/01/2026 | Critical SaaS supplier suffers breach exposing our data | Supplier: CRM platform | C, I | 2 | 4 | 8 | Medium | Ops Manager | Transfer | 5.19, 5.20, 5.22 | DPA in place; supplier security review annually; contractual breach notification within 24h | 28/02/2026 | Open | 06/07/2026
R-003 | 06/01/2026 | Former employee retains access to systems after leaving | User accounts | C, I | 2 | 5 | 10 | Medium | HR Lead | Reduce | 5.18, 6.5 | Leaver checklist with same-day deprovisioning; quarterly access review | 31/01/2026 | In progress | 06/04/2026

## How to use
How to use this template
1. Record each information security risk on its own row. Three worked examples are included; overwrite or delete them.
2. Likelihood and Impact are scored 1 (very low) to 5 (very high). Score and Rating calculate automatically: 15-25 High, 8-14 Medium, 1-7 Low.
3. Choose a treatment option: Avoid (stop the activity), Reduce (add controls), Transfer (insurance/contract), Accept (justify and sign off).
4. Link each risk to the Annex A controls that treat it, and give every risk an owner and a review date.
5. Review the register at least quarterly and after any incident, significant change, or audit finding.
Scoring guidance. Likelihood: 1 = rare (not expected in 5 years), 2 = unlikely (once in 2-5 years), 3 = possible (annually), 4 = likely (quarterly), 5 = almost certain (monthly or more).
Impact: 1 = negligible (no customer or regulatory effect), 2 = minor (internal disruption), 3 = moderate (single customer affected or minor data exposure), 4 = major (multiple customers, reportable breach), 5 = severe (business-threatening incident).